FINAL REPORT

FOR

ORGANIZATIONAL MANAGEMENT SUPPORT

TO

THE NAVAJO NATION

DIVISION OF COMMUNITY DEVELOPMENT

CONTRACT No.C02657

SOW B-3 TASK 8.1

May 31, 2006

Prepared by:

Pacific Western Technologies, LTD

2727 San Pedro Drive N.E., Suite 116 
Albuquerque, New Mexico 87110

TABLE OF CONTENTS

1. PROJECT BACKGROUND	3

2. INTRODUCTION	5

3. OVERVIEW OF THE THREE OFFSITE PLANNING SESSIONS	5

3.1 Key Issues	5

3.2 Critical Factors	7

3.3 Suggested Resolutions	8

3.3.1 Staffing	8

3.3.2 Plan of Operations	9

3.3.3 Policies and Procedures	9

3.3.4  Implement Information Systems	10

3.3.5  Project Classification Scheme	10

4. PROJECT PROCESS AND PROJECT MANAGEMENT	11

5. CURRENT ORGANIZATIONAL CHARTS FOR DCD	11

6.  PHASED APPROACH	14

7.  PHASE I - REALIGNMENT	14

7.1 Proposed DCD Realignment of DES	15

7.2 Proposed DCD Realignment of CDBG	16

7.3 Proposed DCD Realignment of CIO and the LGSC’s	16

CIO	16

LGSC	17

7.4 Staff Qualifications	19

7.5 Timeline	20

7.6 Costs	20

8.  PHASE 2 OPTION - REORGANIZATION	20

8.1 Proposed DCD  - CAP Section	20

8.2 Staff Qualifications	24

8.3 Timeline	24

8.4 Costs	24

9.  PHASE 3 OPTION - RESTRUCTURING	24

9.1 Proposed DCD restructure DES, CIO and CDBG	24

9.2 Proposed Planning Section	25

9.3 Proposed Projects Section	26

9.4 Proposed Contracts and Project Admin	27

9.5 Timeline	28

9.6 Costs	28

10.  SUGGESTED PRESENTATION TO TCDC	28

11.  SUMMARY	28

APPENDIX A	29

APPENDIX B	32

APPENDIX C	34

APPENDIX D	36

APPENDIX E	38

# 1. PROJECT BACKGROUND

Recurring problems may be a symptom of an organization not having clearly thought out what its overall purpose and goals are.  The reorganization of a company or department is usually designed in order to attain greater efficiency and to adapt to changes and the greater needs of the customer.  The Navajo Nation (NN) Division of Community Development (DCD) is taking the initiative to streamline the departments and make the project process more efficient for the community members.  Key staff have recognized this lack of efficiency among the departments and how this has effected project delays and budget constraints.

There are several departments within DCD responsible for the administration, coordination, development, and management of technical services, design, and construction projects.  To efficiently achieve this mission, DCD is required to manage volumes of information, required to implement the Capital Improvement Plan (CIP), and to execute other non-Capital projects.

The Office of the Auditor General (OAG) conducted a review of the NN CIP process in comparison with best practices. This review was requested by the Transportation and Community Development Committee (TCDC). The purpose of the review was to compare the Nation’s current processes against best practices, and to identify areas for improvement. The lack of a reliable and accurate NN CIP raised many concerns and questions about the CIP process.

To assist in achieving the DCD and the CIP mission, Pacific Western Technologies, Ltd. (PWT) was awarded the multi-year technical services contract No.C02657. The contract is a broad general order contract for technical services that included in SOW B-1 the tasks Project Management Needs Assessment and Project Management Review and Assessment and in SOW B-2 a Project Management Prototype System Design (aMap), Project Management System Implementation and Project Management Training on the custom system.  aMap is a PWT developed computer-based management tool that combines the power of relational databases and Geographic Information Systems (GIS). The PWT aMap system customized for DCD is a web-based tool called the WIND Information System. WIND is an acronym for Woven Information of Navajo Data.

Over the course of the past 2-3 years, internal discussions were initiated among the DCD departments regarding a DCD-wide re-organization.  During the Best Practices Review, completed during this time, initial findings of the department’s shortcomings were detailed.  In 2005, with the status of the Conditions of Appropriations (COA) determined, the DCD Departments met with TCDC to discuss PWT’s initial findings and to recommended solutions based on the PWT assessment of the Policies and Procedures for the Design Engineer Services (DES), Capital Improvement Office (CIO) and Community Development Block Grant (CDBG) departments.  TCDC inquired as to what should be done to address the issues from both the Best Practices Review and PWT’s recommendations.  The Best Practices Review was a thorough review of the projects approach for planning and funding, but did not address project execution and closeout

To assist in achieving the CIP mission and to assist in formulating recommendations for project execution and reorganization to the TCDC, DCD issued a Scope of Work (SOW B-3) against the contract No. C02657.  Under SOW B-3, Task 8, PWT was contracted to assist DCD in developing a revised organizational structure for the Division and to make recommendations for change. The initial phase is to consider the CIO, CDBG, and DES Departments.

The approach to the first phase of Task 8 is to conduct three offsite strategic planning sessions, each followed by a compilation of results and findings.  DCD staff participating in the planning sessions includes the Division Director, Department Managers, and other key personnel.

The first planning session was held on April 10th and 11th and included key staff from DES, CIO, CDBG, LGSC and chapter officials.  Preliminary findings and discussion of recommendations based on the review of the reference material concluded key issues and critical factors that have a negative influence on the project process.

The second session was held on April 20 – 21, 2006 and included staff from the Office of Government Development, the Office of the Auditor General, and the Office of Personnel Management.  The final session was held on May 8-9, 2006 and concentrated on Tribal Laws, budget restraints, and political realities that impact the proposed reorganization and identifying resources to staff the proposed organizational structure.

The third planning session was held on May 8th and 9th and included key staff from DES, CIO and CDBG.  This session reiterated any discussions/findings from the 1st two sessions.  Organization charts for a complete restructure of the DCD departments were proposed and discussed in detail with the key staff.  Input from the staff was taken into consideration for this final proposal that included reality both politically and regarding the budget.

An assessment of the following tribal laws has been taken into account in the phased approach for reorganizing the DCD Division:

- Navajo Nation Appropriations Act

- Navajo Procurement Process

- Navajo Nation Purchasing Manual

- Navajo Nation Local Governance Act

The planning sessions draw upon information developed in SOW B-1, assessment, and other relevant studies.  The goal of the planning sessions is to develop standardized definitions, terminology, and understanding of project authorization (for planning, design and construction), initialization, planning, implementation, contracting, and closeout across the departments.  Completion of these goals includes the following deliverables: a suggested reorganized structure, functional job descriptions and qualifications, estimates of capacity and a timeline and estimated costs for reorganization of the three departments.

In SOW B-3 Task 8.2, PWT will conduct assessments of personnel, workflow, business processes, current organization structure, and department capacity for the Departments of Transportation, Solid Waste Management, Housing Services, and the five Local Governance Support Centers (LGSC). The assessment approach will be similar to the assessment completed in SOW B-1 for CIO, CDBG, and DES, but focused on organizational issues rather than process and procedures.

In SOW B-3 Task 8.3, based on results of the assessment conducted under the second phase, will form the baseline for the next step in the reorganization of DCD. The methodology from the Phase 1 DCD Reorganization will be applied to this task. The participants in the strategic planning sessions will include the DCD Division Director, Department Managers, and LGSC and DCD key personnel.

# 2. INTRODUCTION

This document is a summary of meetings held in both Gallup and Albuquerque, New Mexico during the months of April and May of 2006 and is intended to present the final recommendations with options. Participants included Division of Community Development (DCD) Division Director, department managers, and key personnel, in addition to other Navajo Nation (NN) divisions. This is the final document for Task 8.1 of Contract No. 02657 SOW B-3, between DCD and PWT for Organizational Management Support.

# 3. OVERVIEW OF THE THREE OFFSITE PLANNING SESSIONS

An analysis of the three planning sessions identified key issues, critical factors, and suggested resolutions. The summary is presented in the sections below.

## 3.1 Key Issues

PWT identified a series of key issues in the course of completing SOW B-1 and SOW B-2 in addition to the information gathered during the three offsite planning sessions. The Key Issues presented and discussed are listed in the following sections.

- Project Completion

Projects are not completed in a timely manner.

- Priorities

The department’s project priorities change daily.  An example of this could be archaeologists that reside in CIO might have a report due for DES, yet has department priorities that must be met first.  When priorities change, documents tend to get lost.

- Active Project List

Too many projects are on the active list (approx. 600).  There is no definition of what constitutes a project.  Tribal laws contradict each other and departments carry the attitude that they are serving their constituents even at the expense of overloading project staff.

- Communication

There is inadequate communication between departments.  There are turf issues; people choose not to use resources from other departments, causing inefficiencies due to the levels of expertise.

- Technical Oversight

There is a shortage of technical oversight between the departments.  Technically qualified personnel lie within departments that either are not accessible due to the source of funding or due to turf issues.

- Areas of Expertise

Employees are often working outside their levels of expertise due to vacant positions and the lack of a clearly defined chain of command

- Policies and Procedures

Policies and Procedures do not exist or are not being followed.  There is a lack of resources and time to develop policies and procedures, standards, and project controls.

- Expiring Funds

Projects often have expiring funds, which are inadequately tracked, and funds are not being used.  There are no defined Project Managers to track individual funding for projects.  Lack of knowledge and education plays a critical role in accepting projects that should not be on the active project list due to inadequate funding levels.

- LGSC

The LGSC regional offices are unable to provide adequate support to the Chapters in the project preparation process.  Through the LGSC - LGA certification process there is the potential of 230 employees working directly with and within the chapters on certification.  There is a high potential that this staff could assist and train the chapters in project initiation, funding acquisition and project approval.

- Senior Staff

Senior staff are overloaded with projects.  There is a lack of administrative support for senior staff (e.g. the Registered Architect).  Senior staff often spend over 50% of their time engaged in administrative paperwork instead of the duties for which they are certified and qualified.

- Authority

Key personnel within DES lack true project authority; although DES staff are responsible for design, construction, and implementation of projects. Authority lies with the client or with an individual on a part-time basis.  CIO is the client of DES, yet total authority lies with CIO to the exclusion of the department providing the services.

- Local Governance Act

LGSC’s are unable to provide adequate and appropriate assistance to the Chapters on CIP and on project preparation, because most of their resources are dedicated to the chapter certification process under the LGA.

- Planning

Detail is lacking in environmental, landuse, water and utility planning that is required for the preplanning process.  Insufficient information during this early stage of a project could have detrimental effects on the project budget and timeline.

- Project Tracking

There is an insufficient project tracking system currently being utilized involving ad-hoc reports and no follow thru by the project teams and senior staff.  Full implementation of the WIND system will solve this problem.

- Project Management

A lack of employees with the skill set necessary to be a project manager is causing confusion among the departments regarding the project process.  There is not distinction of the preplanning process vs. the design and construction phase of the project.

## 3.2 Critical Factors

For the key issues identified in the preceding section, there is an underlying theme of critical factors that drive all of the key issues. These critical factors include:

- 600 Open Accounts

There are a substantial number of projects on the open accounts list that not adequately funded.

- Staffing

Staffing levels and levels of expertise are inconsistent across the DCD departments.  Skilled technical staff is spread across all departments, causing the complication of shared resources.  Personnel that are either not qualified or who are designated as Project Managers are carrying a heavy workload of projects without the benefit of administrative support, the proper title, authority, and training.

- Decentralization / Chapter Support

The LGSC staff and CIO field personnel are working largely unsupervised.  They have no consistent management, there is no assignment of priorities, and no monitoring or accountability.

- No Clear Definition of An Active Project

There is no clear definition of what constitutes an active, qualified project.

- No Written Criteria for Acceptance of a Project

There are no clearly defined policies and procedures to address acceptance of a project.

This lack of documentation for project requirements has caused the acceptance of 100’s of projects that, in many cases, might have 10% of the appropriated funds to complete the project.  Without policies that determine this criteria, DCD employees have no criteria to deny the acceptance of a project.

## 3.3 Suggested Resolutions

TCDC has required DCD to develop a plan for increasing the efficiency and effectiveness of project execution. Accompanying this directive were suggestions that DCD should restructure or reorganize the division. If it is determined that a DCD restructure or reorganization is the appropriate path forward, there are at least five proposed resolutions that are precursors to a DCD restructure/reorganization. PWT suggests that this approach be presented to TCDC, in addition to any proposed DCD restructure/reorganization. If the TCDC final decision is not to proceed with a DCD restructure/reorganization, these proposed resolutions are essential to increasing the effectiveness of project execution within DCD.

- Augment current DCD staffing with positions suggested in following section.

- Amend the DCD Plan of Operations to accommodate new Policies and Procedures and amend Section II of the Plan of Operations if any reorganization or restructuring of the departments occur.

- Institute the proposed Polices and Procedures provided by PWT as part of the SOW B-1, and develop Policies and Procedures for project definition, project classification, project authorization, and levels of authority for project staff. Create a clear DCD policy for the definition of a project that includes a project classification scheme.

- Implement information systems that support the project process and DCD Policies and Procedures.

### 3.3.1 Staffing

DCD should augment the current staffing plan.  This augmentation would effect only senior staff positions.  The addition of new staff can be accommodated with existing job classifications within the existing NN Department of Personnel Management Class Specifications, with the exception of Project Manager.

The approach presented by PWT included defining: (1) Functional Job Description, (2) Qualifications, and (3) Levels of Authority for the following staff positions:

- Department Manager

- Professional Engineer

- Project Manager

Regardless of the final path forward to increase the efficiency of the project execution process, these positions are critical to success. From presentations and discussions by the Department of Personnel Management’s Human Resources Classification and Pay Manager, all of the staff positions can be added using current class specifications with the exception of the Project Manager position, as indicated above. The process for developing the Project Manager class specification is on the order of 2-6 months. Once the class specification is developed then the position would require authorization and funding before candidates could be interviewed for this critical staff position.

### 3.3.2 Plan of Operations

Under the current DCD Plan of Operations, it will be necessary to amend Section II, if a reorganization or restructure is accepted.  Section II addresses the DCD current structure and departments.  DCD’s current mission is defined so that any changes to the organization’s structure, whether new departments are added or not, will not affect the mission as stated in the Conduct of Operations.

### 3.3.3 Policies and Procedures

Though appropriate Policies and Procedures are critical to any long-term success for DCD, it must be emphasized that writing policies and procedures does not ensure success. The Policies and Procedures are a framework and must be implemented, trained to, and enforced. DCD has made a commitment to implement information systems to support the project process, accountability, and policies and procedures (e.g. ICIP and WIND), but the above argument also applies to the information systems. These are only tools to support the process and must be implemented, trained to, and their usage enforced.

There are policies and procedures that must be finalized and implemented for records management, document management, project management, project definition and project controls.  From the plan of operations, it will flow down to the policies and procedures.

In addition to Policies and Procedures, a standard Administrative Agreement (AA) between DCD departments must be implemented.  These documents should be considered in order to ensure proper documentation and sharing of resources between the departments.  A standard Memorandum of Agreement between the Navajo Nation Departments should also be established.

### 3.3.4  Implement Information Systems

DCD has implemented the WIND information system in order to properly manage project information Under SOW B-3, PWT will work with Real Time Sites to integrate ICIP with WIND Project Management Database. This integration will draw project Scopes of Work, Project Names, Project Numbers, and Funding Sources from the ICIP and make this information available in the WIND Project Management Add New Project Information Screen.

In order for the departments to benefit from the integration of these two information systems (ICIP and WIND), it will be essential for all departments and chapters to populate the databases in a timely and accurate manner to ensure the DCD personnel will have the most efficient means of acquiring data for open CIP and non-CIP projects.   PWPWT is providing DCD with the means of tracking projects; it is up to the department personnel to use it.

### 3.3.5  Project Classification Scheme

An approach to resolve these critical factors, and the cascade of resulting key issues, is for clear DCD Policy on the definition of a project, and the criteria for accepting a project for project execution (e.g. what constitutes “project ready”). To address the approximately 600 open accounts, that are currently considered projects, the suggested approach is to reclassify the accounts/projects. A project classification scheme might include:

- Active Project

- Pending Projects

- Proposed Projects

- Capital Purchases

Active Projects  - all plans and pre-project work in place with >85% of project funding.

Pending Projects  - all plans and pre-project work in place with <85% of project funding.

Proposed Projects  - incomplete project planning and pre-project work and/or minimal funding.

The accounts that fall in the Pending  Projects category could be used for planning and preliminary design work and to obtain next phase funds for project execution. While accounts that fall in the Proposed Projects category could be used for project planning, site selection, or other pre-project work that would provide a basis for securing additional funds for project execution.

# 4. PROJECT PROCESS AND PROJECT MANAGEMENT

On the Navajo Nation, the complexity of the project process, from conception through project execution causes significant confusion.  The funding issues alone can be very complex due to the fact that on most projects multiple funding sources are required.  Currently, all steps in this very complex process are seen as Project Execution.  These steps include: conception, preliminary planning and estimating, environmental and archaeological assessments, funding, final planning, final estimating, contracting, project execution and project closeout.

It is PWT’s opinion that there needs to be two distinct and separate phases to a project; pre-project work and project execution and closeout.  Pre-project work involves such items as land use planning, project conception, preliminary planning estimating and budgeting, acquisition of funds and/or funding sources, and environmental and archaeological assessments.

The reason for this approach is that the pre-project work is more appropriately done at the Chapter/regional level through the Chapter staff, LGSC’s and CIO field personnel.  This would then reserve final planning and estimating, contracting, project execution and closeout for the technical and professional staff within DCD in Window Rock.

By not separating the pre-project work from the project execution the DES staff is totally overloaded with pre-project work and therefore unable to spend enough time on actual project execution much less the development and implementation of proper Policy and Procedure.  By properly applying the LGSC staff and the current CIO field personnel, with some limited assistance from DES, the Chapters can be assisted and guided in the land use planning and pre-project work thereby freeing the DES technical and professional staff to concentrate on project execution, which is where they should be focused.

# 5. CURRENT ORGANIZATIONAL CHARTS FOR DCD

As a quick reference to the current structure of the DCD, the following are the current organizational charts pre-realignment for DES, CDBG and CIO, each having associated position numbers that can be cross referenced to the proposed realignment department charts using the position matrix spreadsheets in Appendix B, C and D:

# 6.  PHASED APPROACH

To achieve a smoother transition for the DCD personnel for the reorganization of the departments, a three (3) phased approach has been recommended.

Phase 1 is the realignment of the DES personnel to assist key staff with administrative support.  This phase will also include the initial transition of the CIO field personnel to be incorporated under the LGSC Agency offices.

Phase 2 Option is the introduction of the Chapter Assistance Program (CAPs) to provide a link between the DCD Projects Office and the Chapters.

Phase 3 Option is the complete restructure of DES, CIO and CDBG after the creation of the CAPs department and is described in more detail in section 9.  This phase introduces new departments that are specific to project processes.

# 7.  PHASE I - REALIGNMENT

Phase I under the SOW B-3, Task 8 addresses each department separately with a summary of current issues and potential solutions.

## 7.1 Proposed DCD Realignment of DES

DES under the current organizational structure has been limited by technically qualified staff and administrative support for these skilled personnel.  The DES senior staff is currently executing the work of project managers, thus not utilizing the skills of the senior staff and not permitting time for development of Policies and Procedures and Project Controls.

The following changes are recommended and noted for the realignment of the DES department:

- Add a Registered Engineer to the current staffing chart.

- The Registered Engineer and Registered Architect should be at the same tier.

- The Office Assistant under Administration should be shifted under the Registered Engineer.

- Administration should report directly to the Department Manager

- Federal Projects should report directly to the Department Manager

- Project Specialist under Administration should be shifted under the Registered Architect.

- One of the Sr. Engineering Technician positions under the Engineering Section should be moved to the Administration Section and identified as IT.

## 7.2 Proposed DCD Realignment of CDBG

The current structure of the CDBG is efficient in managing projects.  The department is funded outside of Navajo Nation’s general funds and is operated entirely by federal HUD funding.  This source of funding has required the department to establish and implement federal standards to meet HUD requirements for project compliance and report submission.

## 7.3 Proposed DCD Realignment of CIO and the LGSC’s

The current structure of the CIO and LGSC’s is inefficient and ineffective.  It is understood that an in depth assessment of the LGSC’s is not scheduled until SOW B-3 Task 8, Phase 2; however, the LGSC’s cannot be ignored in evaluating how chapters and the CIP are supported.  Based on the information and feedback during the three off-site meetings, it has been impossible to ignore the LGSCs and not incorporate them into the reorganization/restructuring recommendations.

## CIO

Under the current organizational structure of the CIO, the following issues have been identified as potential problems involving accountability, workload and lack of controls.

- There are nine levels of reporting directly to the CIO Department Manager

- CIO Field Personnel are not being held accountable.

- Employees are currently being tasked with duties inconsistent with their job titles except for the Department Director and the Administrative Assistant.

## LGSC

Under the current organizational structure of the LGSC the following issues have been identified as potential problems involving accountability, work overload and lack of controls.

- The LGSCs are not being monitored by a single department manager and have no accountability for managing projects, working with the chapters on chapter certification or monitoring of chapter assistance with project funding, initiation, or approval.

- Multiple sources have provided feedback regarding their perception of the LGSCs:

- When the chapters visit the agency offices, the LGSC staff is never available.

- The LGSC staff is rarely seen at the chapters.

- LGSC employees are not properly trained to assist the chapters in some of the duties.

- There is no follow up on projects with the chapters.

There are currently 30 LGSC staff members between the five agencies, and 220 employees at the chapter levels.  That is a significant amount of support staff that can be utilized for the proposed CAP division discussed in the next section.

It is recommended that the Phase 1 realignment move the CIO field personnel under the LGSC as displayed in the following chart.  The purpose of this shift is to add people to assist Chapters with “pre-project” work, such as Land Use Planning and project definition and preparation.

The realignment of the CIO Agency personnel would combine the two agency offices resulting in a CIO realignment chart as follows:

## 7.4 Staff Qualifications

For the success of the realignment it is imperative for the Department Manager, Registered Engineer and Architect to have the added levels of authority:

Registered Engineer

An existing position description exists for a Civil Engineer.  It has been recommended under the first Phase to have a Registered Engineer added to the DES Organizational Chart.

In addition to the existing position description, the following levels of authority and requirements should be considered for this recommended position:

- Authority to delegate administrative duties to personnel

- Authority to hire/fire/review personnel within Engineering Section

- Signature authority over project budgets and contracts within the limits of the project budget.

- Possession of an Engineering License in NM, AZ, or UT or obtain license within one (1) year of employement.

- In addition to Bachelors degree in associated field, applicant must have four (4) years of work in related field in public infrastructure construction.

Registered Architect

In addition to the existing position description, the following levels of authority and requirements should be considered for this recommended position:

- Authority to delegate administrative duties to personnel

- Authority to hire/fire/review personnel within Architect Section

- Signature authority over project budgets and contracts within the limits of the project budget.

Department Manager

In addition to the existing position description, the following levels of authority and requirements should be considered for this recommended position:

- Signature authority over project budgets and contracts within the limits of the project budget.

- Authority to hire/fire/review personnel within Department

- Knowledge of and experience in Engineering and/or Architecture and/or Construction

## 7.5 Timeline

## 7.6 Costs

# 8.  PHASE 2 OPTION - REORGANIZATION

## 8.1 Proposed DCD  - CAP Section

The proposed Chapter Assistance Program (CAP) is envisioned as providing links between the DCD Projects Office and the Chapters. CAP would exist in each of the Agencies and would reorganize the LGSC as previous established from Phase I.  The functional structure of CAP for each agency is shown in the charts below:

The following changes are recommended for the reorganization of the CIO department:

- The Administrative Assistant should be shifted to support the proposed Department Manager for the CAP Section.

CHINLE AGENCY

TUBA CITY AGENCY

SHIPROCK AGENCY

FORT DEFIANCE AGENCY

EASTERN AGENCY

The major function of CAP is to assist the Chapters in both project development and administration including Chapter certification. The Projects function concentrates on education, project planning, CIP compliance, site selection, land withdrawal, applying for and obtaining funds, and project oversight during project execution. CAP is a liaison with the Projects Office Planning Section and the Projects Office Projects Section.  The administrative function concentrates on assisting Chapters with the Five Standards and with Chapter Certification

The components of CAP would be the existing LGSC’s and the CIO field personnel, and would place these groups under a management structure that would ensure priority setting, monitoring and accountability, all of which currently does not exist.  This would also place the existing Planner position in each LGSC under Project Development within the CAP organization.

CAP would continue with the current LGSC tasking of assisting Chapters with Certification, although it is PWT’s suggestion that this function would more logically fall with the Auditor General’s office.

The creation of CAP assists in a partial de-centralization of project preparation and execution and would support additional de-centralization at a later date.

## 8.2 Staff Qualifications

Project Manager

In addition to the proposed position description, the following levels of authority and requirements should be considered for this recommended position:

- Signature Authority over Change Orders not affecting Project Budget.

- Select Suppliers

- Select Staff

- De-select suppliers

- De-select staff

- Influence Supplier Payments / Invoicing

## 8.3 Timeline

## 8.4 Costs

# 9.  PHASE 3 OPTION - RESTRUCTURING

The Phase 3 Option under the SOW B-3, Task 8.1 is proposing a complete restructuring of the DCD departments.  The following sections describe a restructuring that combines three (3) departments into a single department and details the proposed sections.

## 9.1 Proposed DCD restructure DES, CIO and CDBG

The following chart is a graphical representation of the merging of the CIO, CDBG, and DES departments of DCD.

This approach merges the three departments into a single Projects Office and defines four sections within the Projects Office. These sections include:

- Planning

- Chapter Assistance Program (CAP)

- Projects

- Contracts and Project Administration

Reporting directly to the Projects Office Manager is an Administration Section that addresses Projects Office-wide: financials, Policy and Procedure development and maintenance, records management, and document management.

The Contracts and Project Administration section provides contract development, contract compliance, SAS tracking, accounting, project administrative support, and general administrative support to the other sections within the Projects Office.

The manager of the Projects Office is not only responsible for the functional sections, but also serves as the coordinator of project teams, assisting in staff resource allocation, project selection and authorization, and leading the development, implementation and enforcement of Policies and Procedures.

## 9.2 Proposed Planning Section

The structure of the Planning section of the Projects Office is depicted graphically below:

The functions within the Planning Section include:

- Master Planning – technical assistance in project development including planning and estimating, site selection, land withdrawal, and education in the project process for stakeholders and project owners.

- CIP – compliance with Tribal requirements for the CIP and maintenance of Chapter inventories and needs.

- Project Authorization – defines projects acceptance and guides the process for project execution, this function would also concentrate on resolution of the 600 open accounts and the reclassification of projects.

- Grants/Funds Management – this function concentrates on  providing technical assistance in the securing of grants, education, and grant and funding agency client management and compliance.

## 9.3 Proposed Projects Section

The proposed Projects Section of the Projects Office houses the technical expertise of DCD for project execution. The functional structure of the proposed Project Section is shown below.

The Projects section is divided between technical resources (Engineering and Architecture) and Project Management staff. The Project Management staff focuses on Capital Projects, Federal Projects and Special Projects. The Project Managers develop the project team from the section’s technical resources, the Contracts and Projects Administrative section, regulators, and wherever else is appropriate. Projects are not assigned to the Projects Section until they have been authorized as “project ready,” by the Project Authorization group of the Planning Section.

## 9.4 Proposed Contracts and Project Admin

The proposed Contracts and Project Admin would be the contract development, compliance and accounting staff as shown below.

This group’s primary focus is to be advisers and fund managers, however the team can also conduct field reviews. The Contracts and Project Admin is also involved in policy formulation for compliance-related activities.

## 9.5 Timeline

## 9.6 Costs

# 10.  SUGGESTED PRESENTATION TO TCDC

To assure TCDC has been familiarized on the assessment and recommendations for the reorganization and restructuring of the four DCD departments discussed in this documentation, the proposed presentation outline is presented in Appendix E.

# 11.  SUMMARY

In order for this phased approach to be a success top management must be involved.  Change is usually best carried out as a team-wide effort.  Communications about the change should be frequent and with all organization members.  To sustain change, the structures of the organization itself should be modified, including strategic plans, policies and procedures.

The best approach to address resistance is through increased and sustained communications and education.  For example, the leader should meet with all managers and staff to explain reasons for change, how it generally will be carried out and where others can go for additional information.  A plan should be developed and communicated.  Consider holding forums for organization members to express their ideas for the plan.

In consideration of the external factors that will impact the success of any organizational modification to DCD, the reorganization and restructure of DCD may not be achievable in the timeframe set by TCDC. Considerations of the practicality of the approach presented in this report must include the current political climate of the NN (e.g. ensuing presidential election), the reality of budget projections for FY 07 and beyond, the timelines for adding new class specifications, and the change in the DCD business culture required to implement the suggestions presented in the PWT analysis.

PWT suggests, based on current assessment, findings, and analysis that this phased approach be presented to TCDC. This should be presented to suggest that the five proposed resolutions described in Section 3.3 be enacted first, to be followed by the realignment, reorganization and restructure Section 7, 8 and 9.

# APPENDIX A

# PROJECT MANAGER POSITION DESCRIPTION

THE NAVAJO NATION

Project Manager Proposed Position Description

DEFINITION:  Serves as a staff resource with short and long term projects, intended to support services to division members. Develops proposals in support of the divisions, including planning, consultant assessment and supervision, proposal preparation, literature development, constituency outreach and special programs.

ESSENTIAL FUNCTIONS:  This list is ILLUSTRATIVE ONLY and is not a comprehensive listing of all functions and tasks performed by incumbents of this class.

TASKS:

- Carries out ad hoc and ongoing assignments for the project.

- Recruits and organizes volunteers, and consultants as needed, for implementing and completing projects and activities.

- Develops statement of work and budgets for internal review and as appropriate, consideration by prospective outside sponsors and/or bidders. Participates in discussions with outside and inside sponsors with respect to prospective projects.

- Works collaboratively with the department managers to write manuscripts for publication, major reports, committee minutes, and other communications as assigned.

- Provides program management support for select committees, subcommittees, and advisory groups.

- Develops and conducts surveys and needs assessments.

- Develops communication with respect to activities of departments and funded projects.

- Serves as liaison and representative to other organizations as assigned.

- Performs other duties as assigned.

- Manage overall execution of the active project process through project execution and closeout.

- Deliver projects on time and cost within agreed tolerances

- Manage the people, processes and resources involved.

- Establish and update plans with actual and forecast data.

- Escalates decisions on unresolved issues.

- Manage the selection of appropriate core technologies and standards.

- Determine the positions and staffing levels required to complete as scheduled.

- Assign project tasks to staff and monitor results.

- Identify the tasks or other responsibilities that should be assigned to consultants, and advise the necessary team members on the proposed selection and engagement of any consultants that are required.

- Provide regular progress reports to the department and division managers, including analyses that show whether the progress and results achieved are consistent with completion of the project on time and within the assigned budget.

KNOWLEDGE, SKILLS AND OTHER CHARACTERISTICS:

- Possesses exceptional oral and written communication skills.

- Demonstrated team-working abilities and administrative skills.

- Demonstrated ability to work well with many types of people.

- Excellent organizational skills.

- Established record of project management and attention to detail.

- Knowledge of and experience with project management software such as Primavera or Microsoft Project.

- Strong ability to edit work of others.

- Knowledge of methods applied in coordinating, managing, scheduling and controlling multiple phases of projects.

- Knowledge of and understanding of to planning, designing and construction practices.

PHYSICAL REQUIREMENTS AND WORK ENVIRONMENT: Work requires attention to detail with potential exposure to loud noises, dust, toxic chemicals and fumes when working on site.

MINIMUM QUALIFICATIONS:

- College degree with minimum 5 years experience in a field related to engineering/architectural management or construction, or, 8 to 10 years of experience in a related technical field.

- Relevant Project Management Institute (PMI) certification or equivalent.

SPECIAL REQUIREMENTS:

Goal orientation and action-focused, pragmatic and self-disciplined, good at project planning, organizing, communication, team motivation and delagation.

Depending upon the needs of the Nation, some incumbents of the class may be required to demonstrate fluency in both the Navajo and English languages as a condition of employment.

# APPENDIX B

# POSITION MATRIX – PHASE 1

# APPENDIX C

# POSITION MATRIX – PHASE 2 OPTION

# APPENDIX D

# POSITION MATRIX – PHASE 3 OPTION

# APPENDIX E

# TCDC PRESENTATION OUTLINE

To be revised once report content is agreed upon by DCD and PWT.